Present:

Barbara Packer-Muti, Dana Mills, Joycelyn Vogt, Marcia Perez-Del Valle, Mercedes Lardizabal, Ron Ryan, Jacqueline Lytle, Samantha Hull, Kevin Dvorak, Mark Schuknecht, Ale Matias

Minutes and To-Dos:

- Reviewed marketing plan draft

  - Distribution updates:

    - Print will only include posters, ground signs, and table tents (Joycelyn and Marcia to price out these items)

      - 40 posters

      - 13 ground signs

      - 100 table tents

    - Syllabi update/revision to be discussed with Provost (BPM and Kevin)

    - Faculty chair focus groups should be included in plan

    - Promo items (pens and notepads) to be priced out (Joycelyn and Marcia)

  - Promotion updates, discussed asset status:

    - Video shoot underway - all b-roll should be captured by Nov 30

    - Stills need to be captured during shoot (high resolution) – Mark S. will have someone from his staff capturing these

    - Creative will be handled by Ron’s team (Ron needs to price out hours for creative)

    - Need QEP blurb and short description (Jackie is working on this)

    - Begin gathering past writing tips (Jackie and Kevin)

    - Website updates (BPM and Dana)

- Budget needs to be revised (Marcia and Joycelyn)

- Plan Draft, Strategy and Calendar of activities needs to be revised (Marcia)

- Next meeting: Nov 29 to review all assets